KINGLIS / BUSINESS ASSESSMENT / SAMPLE DELIVERABLES

CONFIDENTIAL SAMPLE / FICTIONAL DEMONSTRATION / NOT A FULL  ENGAGEMENT

KINGLIS

BUSINESS ASSESSMENT

Sample Deliverables

BUSINESS PROBLEM  →  EVIDENCE  →  CAUSE  →  PRACTICAL WAY FORWARD

A representative example of how KINGLIS investigates a difficult business problem,
establishes what is actually happening, identifies what is causing it,
and determines what needs to change.

BAS HOLDINGS

Multi-Entity Mining Engineering & Supply Group

| Document type | Status | Use |
| --- | --- | --- |
| Demonstration case | Sample deliverable pack | Capability preview |

CONFIDENTIALITY NOTE — SOS Holdings, its people, evidence, circumstances and findings are fictional. No real client information is contained in this sample.

Understanding precedes change.

KINGLIS / BUSINESS ASSESSMENT / SAMPLE DELIVERABLES

CONFIDENTIAL SAMPLE / FICTIONAL DEMONSTRATION / NOT A CLIENT ENGAGEMENT

THE BUSINESS PROBLEM

Growth was making SOS Holdings increasingly difficult to operate.

SOS Holdings had grown into a multi-entity group. As the business expanded, leadership began experiencing increasing operational friction.

Routine decisions were taking longer. Managers were escalating matters they appeared authorised to handle. Work crossing functions and entities was becoming difficult to close. Senior leaders were repeatedly drawn back into operational decisions.

The symptoms were visible. The cause was not.

THE QUESTION

What is causing SOS Holdings to become increasingly difficult to operate across its entities as the group grows?

WHAT KINGLIS EXAMINED

| Area | What was examined |
| --- | --- |
| Authority | Roles, decision rights, approval pathways and actual decision behaviour |
| Ownership | Responsibility across critical workflows and organizational handoffs |
| Information | How operating information moved between people, functions and entities |
| Organizational memory | Where previous decisions, exceptions and operating context were retained |
| Reporting | Whether management information exposed the causes of delay or only the resulting symptoms |
| Operating reality | How work actually moved compared with how formal structures suggested it should move |

EVIDENCE REVIEWED

Existing organizational records, authority schedules, decision trails, workflow evidence, management reporting, system records and targeted stakeholder interviews.

ASSESSMENT BOUNDARY — Findings relate only to the evidence, people and workflows examined. The assessment does not assume that every process or entity operates in the same way.

EXECUTIVE FINDINGS

The problem is not primarily workload. It is operating ambiguity.

The evidence revealed four connected conditions behind the recurring operational friction.

01 — ACCOUNTABILITY EXCEEDS EXECUTABLE AUTHORITY

Managers were formally accountable for outcomes they could not consistently authorise or close without informal senior confirmation.

| Observed | Implication | Result | Confidence |
| --- | --- | --- | --- |
| In 22 of 31 sampled approval trails, the accountable manager sought confirmation outside the documented approval path. | Delegation existed formally, but decision risk remained concentrated higher in the business. | Routine decisions waited, accountability became blurred and senior leaders remained involved in operational closure. | HIGH |

02 — CRITICAL WORKFLOWS HAVE PARTICIPANTS, BUT NO END-TO-END OWNER

High-friction workflows crossed functions and entities without one person being accountable for the complete outcome.

| Observed | Implication | Result | Confidence |
| --- | --- | --- | --- |
| Purchase-to-pay and project mobilisation involved multiple roles, with ownership changing at each handoff. | Individual responsibilities could be completed while the overall outcome remained unresolved. | Delays, repeated follow-up and escalation became mechanisms for getting work across the line. | HIGH |

03 — CRITICAL OPERATING CONTEXT IS STORED IN PEOPLE

Important decisions frequently depended on experienced individuals reconstructing previous context from memory, messages and personal knowledge.

| Observed | Implication | Result | Confidence |
| --- | --- | --- | --- |
| Supplier history, exceptions and previous commercial decisions could not always be reconstructed from durable organizational records. | The business recorded transactions more reliably than the reasoning behind them. | Growth, absence or turnover increased the likelihood of rework and inconsistent decisions. | MODERATE-HIGH |

04 — REPORTING SHOWS THE SYMPTOM AFTER IT HAS OCCURRED

Management reporting identified late work and aged actions but did not reliably show where work was waiting for authority, information or cross-functional closure.

| Observed | Implication | Result | Confidence |
| --- | --- | --- | --- |
| Leadership could see that something was late without consistently seeing what had made it late. | Management attention was directed toward recovery rather than the conditions producing recurring delay. | Recurring structural friction could therefore appear to be a people-performance problem. | HIGH FOR REPORTS EXAMINED |

THE STRUCTURE BEHIND THE SYMPTOMS

Four findings. One underlying mechanism.

SOS Holdings had distributed work across a larger organization without fully distributing the authority, ownership and organizational knowledge required for that distribution to operate independently.

| UPSTREAM CONDITION | OPERATING MECHANISM | OBSERVED EFFECT |
| --- | --- | --- |
| The business grew and responsibility moved across more functions and entities. | Decision authority remained difficult to exercise, workflows lacked end-to-end ownership and critical context remained concentrated in experienced people. | Escalation, delayed approvals, repeated checking, rework and dependence on senior individuals increased. |

THE CAUSAL PATTERN

GROWTH

↓

WORK DISTRIBUTED ACROSS MORE PEOPLE, FUNCTIONS AND ENTITIES

↓

AUTHORITY, OWNERSHIP AND ORGANIZATIONAL KNOWLEDGE DID NOT DISTRIBUTE AT THE SAME RATE

↓

INFORMAL ESCALATION BECAME THE CLOSURE MECHANISM

↓

DELAY • REWORK • DUPLICATED CHECKING • SENIOR DEPENDENCY

↓

GROWTH CREATED MORE FRICTION INSTEAD OF MORE CAPACITY

WHAT THE EVIDENCE CHANGED

| Initial explanation | What the evidence showed |
| --- | --- |
| Managers already had delegated authority. | Authority existed formally but was not consistently executable in practice. |
| Each department owned its part of the process. | Local responsibility did not create end-to-end accountability. |
| The systems contained the business record. | Systems captured activity more reliably than the reasoning behind important exceptions and commitments. |

KINGLIS CONCLUSION

What appeared to be several separate operational problems was better explained by a smaller number of connected structural conditions.

The problem was not simply that people were busy or that the business had grown. The operating structure supporting that growth had not developed at the same rate.

90-DAY ACTION PLAN

Correct the cause before changing the business around it.

0–30 DAYS — CLARIFY

Make authority usable.

- Confirm decision rights and genuine escalation exceptions.

- Assign one accountable owner to each critical workflow.

- Establish minimum records for material decisions and exceptions.

Evidence of progress: Clear decision rights, workflow ownership and escalation rules.

31–60 DAYS — CHANGE

Run live work through the clarified structure.

- Operate critical workflows under named owners.

- Apply the revised decision and escalation pathways.

- Track where work is blocked by authority, information or handoffs.

Evidence of progress: Live work moves without informal shadow processes.

61–90 DAYS — VERIFY

Establish whether the change is working.

- Measure escalation rates and approval delays.

- Identify and close remaining ownership or authority gaps.

- Embed effective controls into normal management routines.

Evidence of progress: Reduced escalation, faster decisions and clearer ownership.

WHAT SHOULD NOT CHANGE YET

| Do not change yet | Why |
| --- | --- |
| Group-wide restructure | The evidence does not establish the organization chart as the primary cause. |
| ERP or workflow platform replacement | Automating unclear authority and ownership would risk automating the ambiguity. |
| Additional management layers | More managers could create more handoffs without resolving decision closure or end-to-end ownership. |

EXECUTIVE PRIORITY — Fix the operating conditions producing the friction before adding structure, systems or headcount to compensate for it.

THE ANSWER

From business problem to clear next step.

WHAT APPEARED TO BE HAPPENING

SOS Holdings was becoming harder to operate as it grew. Routine work was taking longer, managers were escalating decisions and senior leaders were increasingly involved in operational closure.

WHAT THE EVIDENCE ESTABLISHED

Growth had distributed work across a larger business without sufficiently distributing the authority, ownership and organizational knowledge needed to support it. The visible problems were symptoms of those underlying conditions.

WHAT NEEDED TO CHANGE

Leadership needed to make decision rights executable, establish end-to-end ownership for critical workflows and preserve material decision context within the organization.

WHAT DID NOT NEED TO CHANGE YET

The evidence did not support beginning with a group-wide restructure, new ERP platform or additional management layer.

WHAT LEADERSHIP COULD NOW DO

Leadership had a defensible explanation of the problem, a clear set of priorities and a controlled 90-day sequence for addressing the conditions producing it.

WHAT THE CLIENT RECEIVES

| 01 | Executive Findings Report |
| --- | --- |
|  | A clear account of what the evidence establishes, the material findings, their implications and the priorities arising from them. |

| 02 | Structural Intelligence Map |
| --- | --- |
|  | A visual explanation of how the findings connect and what is producing the observed problem. |

| 03 | 90-Day Action Plan |
| --- | --- |
|  | A sequenced set of priorities for the first 30, 60 and 90 days — including what should deliberately not change yet. |

| 04 | Executive Findings Meeting |
| --- | --- |
|  | A confidential 60-minute discussion of the findings, evidential confidence, implications and available next steps. |

THE PURPOSE OF A BUSINESS ASSESSMENT

A Business Assessment does not attempt to diagnose the entire organization. It investigates one agreed business problem or question, examines the parts of the business materially connected to it, and establishes the clearest explanation the available evidence responsibly supports.

Find out what's really causing the problem.

Understanding precedes change.

CONFIDENTIAL SAMPLE / FICTIONAL DEMONSTRATION / NOT A CLIENT ENGAGEMENT

KINGLIS / BUSINESS ASSESSMENT / SAMPLE DELIVERABLES

CONFIDENTIAL SAMPLE / FICTIONAL DEMONSTRATION / NOT A CLIENT ENGAGEMENT